## Sheet1
High Level | Detailed Steps | Start Date | End Date | Status | Resource | Comments
Data Source Identification
| Epidemic | 2020-02-29 | 2020-03-02
Zika
Corona Virus
Ebola
Cholerea
SARS
| Share Market Data | 2020-02-29 | 2020-03-02
Nasdaq
Dow Jones
London Stock Exchange
ETL
| Data Extract | 2020-03-01 | 2020-03-03 |  |  | Basic code for one or two Epidemic, which can be reused for all
| Data Transform | 2020-03-01 | 2020-03-03
| Data Load | 2020-03-01 | 2020-03-03
Flask Application
| Design | 2020-03-02 | 2020-03-03
| Development | 2020-03-04 | 2020-03-06
HTML
| Design of web page | 2020-03-02 | 2020-03-02
Development of web page
Java Script
Design of Java Script (Basic flow)
Development of basic flow
D3.Js
Selection of a graph
| Design of the graph | 2020-03-02 | 2020-03-03
Development of Graph
for Epidemic
for stock market
Mapping
Selection of Map
Collecting the coordinates
Selection of mapping library
| Design of Map | 2020-03-02 | 2020-03-03
Development of Map
Integration of all components
| Integrate all components | 2020-03-07 | 2020-03-09
Testing and confirming |  | 2020-03-09 | 2020-03-09
Fixing issues if any |  | 2020-03-10 | 2020-03-11
Presentation
| Design of PPT - Sections, contents etc.. | 2020-03-08 | 2020-03-08
| Develop the PPT | 2020-03-09 | 2020-03-11
Final Presentation |  | 2020-03-14 | 2020-03-14